## MAIN
TASK | ASIGNEE | NOTES | CURRENTLY WORKING ON | PERCENTAGE COMPLETE | COMPLETED
- create custom post types and taxonomies |  |  |  |  | YES
- create static pages |  |  |  |  | YES
- create main and footer menus pulling in correct pages |  |  |  |  | YES
- fix listing widget so we can display recent posts on pages | MITTAL | - I can't seem to figure out how to get this working |  |  | YES
- add events with events plugin | MITTAL |  |  |  | YES
- create forms | GLEN | Decision to be made on Gravity forms or Ninja Forms (keeping in mind forms will need the ability to add ecommerce (payments) |  |  | NO
- create Blog list and detail views | GLEN | Blog can use the base "post" content type |  |  | NO
- fix sidebar menu functionality to display prooper content cased on page you are on | MITTAL | - right now contains static content |  |  | NO
- put in dummy content for testing | GLEN | Content entry will be done by client - however some may be added for testing purpose. We will need to port over some legacy content such as events / news posts |  |  | NO
- create site wide search functionality | MITTAL |  |  |  | NO
- home page CTA's | GLEN |  |  |  | NO
- sidebar nav CTA's | MITTAL |  |  |  | NO
- widgets | MITTAL | - recent post widgets, social share widget |  |  | NO
- create library site |  | library to be ported from current site, theme updated to inherit most site styles with a separate header and footer for library |  |  | NO
- create USMC Portal site |  | - see page 9 in A&DD |  |  | NO
- create landing page templates | GLEN |  |  |  | NO
- ecommerce components |  | Simple product store / cart and payment processing (square is providor for gateway) |  |  | NO
- creating calls to actions and widgets |  | - see page 8 in A&DD |  |  | NO
Advanced Roles & Permissions | GLEN | Site and subsites will require advanced roles (main admins with full publish capability / editors with no or limited publish capability defined by content type section or page and email notifications for approvals) |  |  | NO
- update main page template to ensure correct information is available for client to enter |  |  |  |  | NO
- make theme "client proof" | GLEN | - by "client proof" I mean take out any way for client to mess up styling, disable them from seeing updates and code editor and so on |  |  | NO
- Resources CPT |  |  |  |  | YES
- Employment CPT |  |  |  |  | YES

## Glen
- fix in page name title items to cut off at certain character number
- fix masthead images to scale properly
- ajax load more on profiles page
- issue with logo in main nav
- Do we allow comments??
- fix page elements ie accordion, intro title etc.
- file upload time view details?? What is this supposed to show??
- grey box on 404 page out of wack
- flexbox issue in main menu, last item
- mobile styles
- make sure all pages have rendom masthead or featured image function
- update all accordions to div in stead of P tag to support WSYWIG editors
- how to deal with block quotes
- add in fake txonomies for testing and building filters
- align read more buttons in card view to bottom
- update all custom fields with instructions
- fix links in program cards
- mobile menu search
- style events plugin
- need to pull in a list of courses to the bottom of program page
- restrict home page widget to certain post types
- Style CTA widget
- finish program card detail view
- test differnt upcoming posts in below content footer area
- do we hide widgets that we dont want them to use??
- put in correct colours in CTA widget
- put in extra fields from client deck provided

## Mittal
- fix sidebar nav menu, some pages just showing a line
- Update Instagram plugin with proper directional arrows
- XLS upload issues
- ajax load more at bottom of pages ie courses and programs
- ical download on events page
- url issues (talk to glen about this)